APPENDIX 1

INTERNAL AUDIT PLANS 2019/20

SOUTH RIBBLE COUNCIL

| WORK AREA | RISK | EST (Days) | ACT | BAL | REVIEW STATUS | ASSURANCE RATING | STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AUDIT PLANNED WORK |
| Areas of work to be identified |  | 60 | 0 | 60 |  |  |  |
| RESOURCES & TRANSFORMATION |
| Legal |
| HR |
| Absence Management | Medium | 10 | 0 | 10 |  |  |  |
| Democratic Services |
| Ethical Culture Review | High | 10 | 0 | 10 |  |  |  |
| Customer & Digital |
| ICT Review | High | 20 | 3.3 | 16.7 |  |  | Meeting with MIAA to agree areas to be reviewed and assessment of audit work previously undertaken within ICT |
| GDPR Compliance Reviews | High | 10 | 16.2 | -6.2 | Ongoing |  | Further compliance reviews undertaken to cover additional areas |
| Council Tax | High | 5 | 0 | 5 |  |  |  |
| NNDR | High | 5 | 0 | 5 |  |  |  |
| Housing Benefits | High | 5 | 0 | 5 |  |  |  |
| Finance |
| Income Collection & Receipt | High | 25 | 0 | 25 |  |  |  |
| Credit Cards | High | 10 | 14.1 | -4.1 | Draft report |  | Report is with Acting Principal Auditor for review |
| REGENERATION & GROWTH |
| Neighbourhoods & Development |
| My Neighbourhood Processes | High | 10 | 0 | 10 |  |  |  |
| Environmental Enforcement | High | 15 | 0 | 15 |  |  |  |
| Leases / Licences to Community Centres etc. | High | 10 | 0 | 10 |  |  |  |
| Parks & Neighbourhoods |
| Car Park Management / Enforcement | High | 10 | 3.5 | 6.5 | Commenced |  | Audit testing on-going, expected completion October 2019 |
| Tree Inspections & Maintenance | High | 10 | 0 | 10 |  |  |  |
| Planning & Property |
| TOTAL PLANNED WORK |  | 215 | 37.1 | 177.9 |  |  |  |

| UNPLANNED WORK |
| --- |
| Performance Management Information (additional work) |  |  | 4.4 | -4.4 | Ongoing |  | Additional work being undertaken to review Key Performance Indicators and Data Quality Policy |

| ONGOING WORK THROUGHOUT THE YEAR |
| --- |
| CORPORATE AREAS |
| Annual Governance Statement | N/A | 20 | 13.1 | 6.9 |  |  | Audit input provided in collating information to inform the Annual Governance Statement |
| Assurance Mapping | N/A | 10 | 4.5 | 5.5 |  |  |  |
| Anti-Fraud & Corruption | N/A | 10 | 0 | 10 |  |  |  |
| NFI | N/A | 5 | 0.4 | 4.6 |  |  | Preparation for the Council Tax Single Person Discount / Electoral Register exercise later this year |
| Corporate Complaints | High | 10 | 8.2 | 1.8 |  |  | Complaints processes reviewed as part of ongoing investigation work |
| Governance Committee | N/A | 10 | 2.5 | 7.5 |  |  |  |
| Total Corporate Areas |  | 65 | 28.7 | 36.3 |  |  |  |
| PROJECT SUPPORT |
| HR and Payroll system update | Project |  | 0.2 |  | Project Support |  |  |
| InPhase Development | Project |  | 2.4 |  | Project Support |  |  |
| Project Support Total Days |  | 20 | 2.6 | 17.4 |  |  |  |
| GDPR Implementation | Project | 5 | 4.6 | 0.4 | Project Support |  | Increased Audit presence within project group |
| Project Support Totals |  | 25 | 7.2 | 17.8 |  |  |  |
| TOTAL ONGOING WORK |  | 90 | 35.9 | 54.1 |  |  |  |
| OTHER WORK |
| Residual Work from 2018/19 |
| Commercial Properties | N/A |  | 4.6 |  | Completed | Limited | Previously reported |
| Health & Safety | N/A |  | 12.9 |  | Completed | Adequate | Previously reported |
| Project Management | N/A |  | 1.9 |  | Completed | N/A | Work undertaken now incorporated into project support due to development of InPhase. |
| Residual Work Total Available Days |  | 10 | 19.4 | -9.4 |  |  |  |
| GENERAL Areas |
| GRACE System Administration | N/A | 10 | 0 | 10 |  |  |  |
| Post Audit Reviews | N/A | 5 | 0.3 | 4.7 |  |  |  |
| General Areas Total Available Days |  | 15 | 0.3 | 14.7 |  |  |  |
| Contingency / Irregularities |
| Contingency / Investigations / Irregularities |  |  | 60.6 |  | Ongoing |  | Work mainly undertaken by Interim Head of Shared Assurance |
| Contingency/Irregularities Total Available Days |  | 10 | 60.6 | -50.6 |  |  |  |
| TOTAL OTHER PLAN |  | 35 | 80.3 | -45.3 |  |  |  |
| TOTALS |  | 340 | 157.7 | 182.3 |  |  |  |

SHARED FINANCIAL SERVICES

| WORK AREA | RISK | EST (Days) | ACT | BAL | REVIEW STATUS | ASSURANCE RATING | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AUDIT PLANNED WORK |
| Creditors | High | 20 | 14.8 | 5.2 | Ongoing |  | Testing ongoing, expected completion October 2019 |
| Financial Systems; | High | 20 | 0 | 20 |  |  |  |
| Procurement | High | 30 | 0 | 30 |  |  |  |
| Money Laundering | High | 20 | 0 | 20 |  |  |  |
| NFI Data Matching Reviews of Financial Matches inc. Creditors / Payroll / Housing Benefits | Medium | 10 | 10.2 | -0.2 | Draft report |  | Work undertaken on Creditors & Payroll matches re: employees, Draft report to be reviewed |
| Total Planned Work |  | 100 | 25 | 75 |  |  |  |

| UNPLANNED WORK |
| --- |
| Shared Services Review of Accounts |  |  | 7 | -7 | Draft report |  | Report is with Interim Head of Shared Assurance for review |
| Total Unplanned Work |  |  | 7 | -7 |  |  |  |

| OTHER WORK |
| --- |
| General Areas |
| GRACE System Administration | N/A | 5 | 0.2 | 4.8 |  |  |  |
| Post Audit Reviews | N/A | 5 | 0 | 5 |  |  |  |
| Total General Areas |  | 10 | 0.2 | 9.8 |  |  |  |
| Residual Work from 2018/19 |
| Cash & Bank |  |  | 11.5 |  | Completed | Substantial | 2 minor areas of control weakness identified, no materiality |
| Treasury Management |  |  | 1.1 |  | Completed | Substantial | 4 minor areas of control weakness identified, no materiality |
| Payroll |  |  | 2.9 |  | Draft report |  | Awaiting agreement of Management actions. |
| Main Accounting |  |  |  |  | Completed | Substantial | 1 area of control weakness identified, no materiality |
| Total Residual Work |  | 5 | 15.5 | -10.5 |  |  |  |
| Contingency / Irregularities |
| Total Contingency / Irregularity Work |  | 5 | 0 | 5 |  |  |  |
| TOTALS |  | 120 | 47.7 | 72.3 |  |  |  |