Update on Recommendations made at previous Scrutiny Meetings

| Date & Min | Recommendation | Lead Member | Lead Officer | Accepted? | Implemented? | Completed? | Progress/Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 04/07/19  Min 4.3 | The report commissioned by the Leader on the Civic Centre commercialisation spending be brought to a future meeting of the Committee. | Leader of the Council | Neil Anderson | yes | No | No | Report will come to Cabinet and Scrutiny in early 2021. The delay has been down to the Covid Crisis |
| 04/07/19  Min 4.4 | The Committee will be provided with updates on the masterplans and rephasing and resourcing them. | Planning, Regeneration and City Deal | Jonathan Noad | Yes | Partially | No | Tenders for appointing an urban design consultancy will be issued for Penwortham Town Centre in Q3 2020/21 with the aim of the work being undertaken during 2021. Other centres will be covered in future financial years.  Work on the Leyland Town Deal is progressing at a pace and the Board have prepared a draft Town Investment Plan (TIP). The TIP was supported by SRBC Full Council on 30th September 2020. Consulation and engagement on the projects in the TIP is ongoing at present. The Board are due to submit their TIP to Government by the end of October 2020. |
| 14/11/19  Min 24 | The masterplans for every town centre be circulated to members via email. | Planning, Regeneration and City Deal | Jonathan Noad  Neil Anderson | Yes | No | No | The draft Leyland Masterplan was part of the agenda for Cabinet in January 2020. Copies have also been made available in Members resource rooms.  More recently the draft Leyland TIP was in Full Council papers for September.  Other centre masterplans have not yet been prepared. |
| 14/11/19  Min 25.2 | The Scrutiny Committee considers the future options for the management of leisure facilities in the future | Health, Wellbeing and Leisure | Neil Anderson | Yes | In progress | No | Report is going to Cabinet on 14th October on a future Leisure Facilities Strategy which include looking at options for future management of Leisure Facilities |
| 14/11/19  Min 25.7 | Delivery plans for 2019 be amended to include more quantifiable measures of success | Health, Wellbeing and Leisure | Neil Anderson | Yes | In progress | No | Are there copies of delivery plans for me to be able to amend? We can add more performance indicators to measure success. |
| 14/11/19  Min 25.8 | The Council considers developing a Leisure and Public Health Strategy to take a more holistic, strategic and integrated approach with partners to include mental health, prevention and youth engagement. | Health, Wellbeing and Leisure | Neil Anderson | Yes | Working with partners | No | Neil will speak to Howard & Jennifer about this. |
| 13/02/20  Min 43.1 | The Scrutiny Committee encourages the council to work towards being a Living Wage employer with its contractors. | Leader | Gail Collins |  | In progress |  | This forms part of the Corporate project to become an accredited Living Wage employer. As detailed within the project scope this particular recommendation will be picked up as part of a review and changes to Procurement policies. |
| 13/02/20  Min 43.3 | The Scrutiny Committee requests a copy of the audit findings from the review of leisure centre costs at the appropriate time. | N/A | Janice Bamber |  |  |  |  |
| 13/02/20  Min 43.6 | The Scrutiny Committee looks forward to receiving an evaluation of the new youth support funding as it progresses. | Health, Leisure and Wellbeing | Jennifer Mullin | Yes | No | No | The project is in its infancy and recruitment of additional officers in both sports’ development and the co-ordinator’s role has begun. Evaluation of the new youth support funding will take place once the programme progresses over the next few months. |
| 09/07/20  Min 8.1 | Regular updates from the Council’s consultants on Worden Hall be provided to the Committee. | Finance, Property and Assets | Jonathan Noad  Neil Anderson | yes | yes | No | Work in preparing the planning and listed building consent applications is ongoing with them due to be submitted in November 2020. |
| 09/07/20  Min 8.2 | A further update on the procurement process for the Hall be provided to the Committee. | Finance, Property and Assets | Jonathan Noad  Neil Anderson | yes | yes | No | Regular updates will be brought to Scrutiny committee on the Worden Hall project. The procurement of the refurbishment will be undertaken following the securing of planning permission. |
| 09/07/20  Min 8.3 | Information on the costs involved with the Council’s consultants for Worden Hal be provided to the Committee. | Finance, Property and Assets | Jonathan Noad  Neil Anderson | yes | yes | No | A note of the procurement, costs and authorisations will be provided to a future Scrutiny meeting. |
| 09/07/20  Min 9.3 | The Committee requests consideration be given to a planning policy on hot food takeaways in light of the Director of Public Health’s advice | Planning, Regeneration and City Deal | Jonathan Noad | yes | In progress | no | This will be considered as part of the new Central Lancashire Local Plan process. Consideration will be given to whether a Supplementary Planning Document can be prepared in advance. |
| 09/07/20  Min 9.4 | An update on the homelessness strategy be provided to members | Planning, Regeneration and City Deal | Jonathan Noad | yes | In progress | no | A new Homelessness Strategy has recently been approved by Cabinet in September 2020. The Homelessness Strategy provides an action plan. A future report can be brought to Scrutiny to provide progress on the implementation of the action plan. |
| 09/07/20  Min 9.5 | The Committee welcomes the offer of visiting the extra care facility in Chorley and would like this arranged. | Planning, Regeneration and City Deal | Jonathan Noad | yes | no | no | This can be arranged once COVID measures are relaxed sufficiently. |