Update on Recommendations made at previous Scrutiny Meetings

| Date & Min  | Recommendation  | Lead Member  | Lead Officer  | Accepted?  | Implemented?  | Completed?  | Progress/Comments  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 04/07/19 Min 4.3  | The report commissioned by the Leader on the Civic Centre commercialisation spending be brought to a future meeting of the Committee.  | Leader of the Council  | Neil Anderson  |  yes |  No |  No | Report will come to Cabinet and Scrutiny in spring 2021. The delay has been down to the Covid Crisis which is now into a second lock down. It is unlikely that we will be able to have events in the Civic Centre until the spring at the earliest. This project therefore has been put back |
| 04/07/19 Min 4.4  | The Committee will be provided with updates on the masterplans and rephasing and resourcing them.  | Planning, Regeneration and City Deal  | Jonathan Noad  | Yes  |  Partially | No | Tenders for appointing an urban design consultancy will be issued for Penwortham Town Centre in Q3 2020/21 with the aim of the work being undertaken during 2021. Other centres will be covered in future financial years.Work on the Leyland Town Deal is progressing at a pace and the Board have prepared a draft Town Investment Plan (TIP). The TIP was supported by SRBC Full Council on 30th September 2020. Consulation and engagement on the projects in the TIP is ongoing at present. The Board are due to submit their TIP to Government by the end of October 2020. |
| 14/11/19Min 24 | The masterplans for every town centre be circulated to members via email. | Planning, Regeneration and City Deal | Jonathan NoadNeil Anderson | Yes | No | No | The draft Leyland Masterplan was part of the agenda for Cabinet in January 2020. Copies have also been made available in Members resource rooms.More recently the draft Leyland TIP was in Full Council papers for September. The TIP has been submitted on 30 October to MHCLG |
| 14/11/19Min 25.2 | The Scrutiny Committee considers the future options for the management of leisure facilities in the future | Health, Wellbeing and Leisure | Neil Anderson | Yes | In progress | No | Report is going to Cabinet on 14th October on a future Leisure Facilities Strategy which include looking at options for future management of Leisure FacilitiesFurther work is taking place looking at potential Management options ready for post March 2021. Leisure Facilities Strategy has now been adopted |
| 14/11/19Min 25.7 | Delivery plans for 2019 be amended to include more quantifiable measures of success | Health, Wellbeing and Leisure | Neil Anderson | Yes | In progress | No | Are there copies of delivery plans for me to be able to amend? We can add more performance indicators to measure success.  |
| 14/11/19Min 25.8 | The Council considers developing a Leisure and Public Health Strategy to take a more holistic, strategic and integrated approach with partners to include mental health, prevention and youth engagement. | Health, Wellbeing and Leisure | Neil Anderson | Yes | Working with partners | No | Neil will speak to Howard & Jennifer about this. This will also need to include Cultural and Arts activity and the contribution it can  |
| 13/02/20Min 43.1 | The Scrutiny Committee encourages the council to work towards being a Living Wage employer with its contractors. | Leader | Gail Collins |  | In progress |  | This forms part of the Corporate project to become an accredited Living Wage employer. As detailed within the project scope this particular recommendation will be picked up as part of a review and changes to Procurement policies.  |
| 13/02/20Min 43.6 | The Scrutiny Committee looks forward to receiving an evaluation of the new youth support funding as it progresses. | Health, Leisure and Wellbeing | Jennifer Mullin | Yes | No | No | The project is in its infancy and recruitment of additional officers in both sports’ development and the co-ordinator’s role has begun. Evaluation of the new youth support funding will take place once the programme progresses over the next few months. |
| 09/07/20Min 8.2 | A further update on the procurement process for the Hall be provided to the Committee. | Finance, Property and Assets | Jonathan NoadNeil Anderson | yes | yes | No | Regular updates will be brought to Scrutiny committee on the Worden Hall project. The procurement of the refurbishment will be undertaken following the securing of planning permission. |
| 09/07/20Min 8.3 | Information on the costs involved with the Council’s consultants for Worden Hall be provided to the Committee. | Finance, Property and Assets | Jonathan NoadNeil Anderson | yes | yes | No | A note of the procurement, costs and authorisations will be provided to a future Scrutiny meeting. |
| 09/07/20Min 9.5 | The Committee welcomes the offer of visiting the extra care facility in Chorley and would like this arranged.  | Planning, Regeneration and City Deal | Jonathan Noad | yes | no | No | This can be arranged once COVID measures are relaxed sufficiently. |
| 22/10/20Min 19.3 | Consultation on the Community Wealth Building Action Plan be undertaken with business organisations, such as the Federation of Small Businesses, the Institute of Directors and the Confederation of British Industry. | Community Engagement, Social Justice and Wealth Building | Jonathan Noad | Yes | Partly | No | A business engagement meeting was held following the previous Scrutiny Meeting and further engagement is being considered but is limited due to COVID. |
| 22/10/20Min 19.6 | The final draft of the action plan be presented to Full Council following a Member Briefing. | Community Engagement, Social Justice and Wealth Building | Jonathan Noad | Yes | No | No | In progress |
| 22/10/20Min 19.7 | More explicit links be made between the Community Wealth Building Action Plan and the Community and Health and Wellbeing Strategies. | Community Engagement, Social Justice and Wealth Building | Jonathan Noad | Yes | No | No | In progress |
| 22/10/20Min 19.8 | Information on the Council’s land ownership be provided to a future meeting. | Finance, Property and Assets | Jonathan Noad | No | N/A | N/A | Further clarification sought on what was requested by the committee. Further update will be provided to a later meeting.  |
| 22/10/20Min 21.2 | Details of car parking arrangements be included in the Worden Hall project update at the next meeting.  | Finance, Property and Assets | Neil Anderson | yes | no | no | A revised plan of car-parking has been developed following consultation with Planning. This will involve a car park extension rather than a new carpark .This will form part of the planning application that will go in in early December |