| Date & Min | Recommendation | Lead Member | Lead Officer | Accepted? | Implemented? | Completed? | Progress/Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 22/03/21  Min 33.5 | The costs associated with refurbishing Penwortham Leisure Centre be provided to members | Finance, Property and Assets | Mark Lester | Yes | No | No | Significant changes/opportunities have arisen within the last few months on this project. With the transfer from Serco contractual delays and planned PAISA works covered pool sites boilers and filter service/replacement, Penwortham sports hall floor resurfacing.  An opportunity for Decarbonisation funding has lead us to delay related heating, air handling and energy saving work to see if we can leverage grant funding. A survey was undertaken last week and a report is due which will be used for the funding bid.  As a result we are concentrating on 3 priority schemes.   * Bamber Bridge Tennis centre car park extension (estimate £188k) planned start mid summer * Leyland, Bamber bridge and Penwortham external painting – Low Level works ongoing and Penwortham and Bamber bridge high level access works going out to tender soon * Refurbishment of Bamber Bridge and Penwortham Reception areas – Options are be sought for reconfiguration and extension options, planned works for a December finish to align with quieter trading. |
| 13/09/21  Min 46.3 | The new single strategic partnership between Chorley and South Ribble be scrutinised in the future and the potential for joint scrutiny with Chorley Council be explored | Leader of the Council | Howard Anthony | Yes | Yes | No | Chorley and South Ribble Partnership will be happy to provide updates and reports to the scrutiny committee as required and requested. We will work with democratic services to arrange the process for this. |
| 13/09/21  Min 46.4 | The key performance indicator for fuel poverty be reviewed as part of the next refresh of the corporate strategy | Leader of the Council | Howard Anthony | Yes | No | No | This will be completed as part of the refresh of the corporate strategy and completed by the end of the current calendar year. |
| 13/09/21  Min 46.5 | Asks that further information on the number of young people engaged in the community conversations be provided | Communities, Social Justice and Wealth Building | Jennifer Mullin | Yes | Yes | Yes | 32 young people were engaged during the Community Conversations and a separate 17 were engaged during a specific young person session regarding the Youth Council and Mental Health. |
| 13/09/21  Min 46.6 | Asks that further examples of the outcomes from the community hubs be included in future reports with the proposed evaluations of success | Communities, Social Justice and Wealth Building | Howard Anthony | Yes | No | Yes | From quarter two reporting, this will be included in future reports. |
| 13/09/21  Min 46.8 | Asks that future reports include information on credit union take-up rates | Finance, Property and Assets | Howard Anthony | Yes | Yes | Yes | Quarterly reporting is in place with the credit union and data will be provided within the monitoring reports from quarter 2. |
| 13/09/21  Min 46.9 | Requests an update on the pre-planning advice services resuming | Planning, Business Support and Regeneration | Jonathan Noad | Yes | N/A | Yes | The pre-app advice for major applications is taking place. In terms of minor applications, this is still being kept under review as individual officers’ workloads remain high, as do application submissions along with the fact we are currently processing some very large and complex major applications. |
| 13/09/21  Min 46.9 | Requests an update on current customer service response times | Leader of the Council | Asim Khan | Yes | N/A | Yes | This was provided to members of the Panel via email on 27 September 2021. |
| 13/09/21  Min 47.4 | Asks for an update on the timescales involved in completing Birch Avenue Playground | Health and Wellbeing | Jennifer Mullin | Yes | N/A | No | It is aimed to have the playground completed before the end of March but this is caveated on the supply of play equipment. |