| REPORT TO | ON |
| --- | --- |
| Governance Committee | 14 March 2019 |
| TITLE | REPORT OF |
| Internal Audit Progress Report as at 1 March 2019 | Interim Head of Shared Assurance |

| Is this report confidential? | No |
| --- | --- |

# PURPOSE OF THE REPORT

# To provide the Governance Committee with a summary of Internal Audit work undertaken for South Ribble and the Shared Services element for the period 1 April 2018 to 1 March 2019

# RECOMMENDATIONS

2.1	 Members are asked to consider and note the contents of the report

# EXECUTIVE SUMMARY

Governance Committee are required to be informed of and review Internal Audit work as part of their review of the Council’s internal control environment and overall Governance arrangements.  To that end the report outlines the work undertaken for the period 1 April 2018 to 1 March 2019 and the individual opinion of the internal control environment of those pieces of work.  The attached document outlines the progress of work up to the 1 March 2019 and the remaining work expected to be completed by the 31 March 2019

Detailed information in regard to progress against individual areas of work / auditable areas has been provided at Appendix 1.

# CORPORATE PRIORITIES

# The report relates to the following corporate priorities:

| Excellence and Financial Sustainability | X |
| --- | --- |
| Health and Wellbeing |  |
| Place |  |

Projects relating to People in the Corporate Plan:

| People |  |
| --- | --- |

5.   	BACKGROUND TO THE REPORT

- This is the progress report of work undertaken for the 2018/19 Plan, which was previously agreed with the Governance Committee

6.   	PROPOSALS (e.g. RATIONALE, DETAIL, FINANCIAL, PROCUREMENT)

6.1	Appendix 1 identifies the status of each piece of work / audit review and stage the audit review is at, e.g., Scope identified and agreed; Draft Report completed and with Interim Head of Shared Assurance for review etc.  The report has been produced in this way in order to outline to Members the actual status of each area of work and the progress made since the last report.  The report outlines completed work and their assurance rating.  In that regard, the assurance rating is based on the four levels of assurance previously agreed; Limited, Adequate, Substantial and Full.  The report has also been reorganised to outline in Sections, Audit Planned Work, Work that is ongoing throughout the year, such as Project Groups Residual Works and work outside the normal planned work such as GRACE Administration work, Business Continuity etc.

6.2	Significant progress has been made against the Audit Plan in the last 2 months, however, as has previously been notified to this Governance Committee the section has suffered from resource issues throughout the 2018/19 Plan Year.  The attached Appendix outlines that in regard to South Ribble Council there are 91.4 days completed and 27.8 days work remaining for planned audits, this shows that by the end of March Internal Audit will have completed 74.5% of planned audit work in Year.  With work carried forward 97% of the 2018/19 Audit Planned Work will be completed albeit not in the 2018/19 Financial Year.  The Appendix also shows where planned days have not been utilised due to early completion of work or, as with project work the reduction in audit support due to resource issues already reported to this Committee.  The overall completion of the plan is calculated at 78%.

6.3	As can be seen from Appendix 1, substantial progress has been made however, there are a small number of audit reviews that have had to be rearranged, some due to operational service issues and some due to Audit resource issues.

The following audits have been agreed to be carried forward into 2019/20 due to operational service issues:-

- My Neighbourhoods – this is due to a full service review being undertaken and new processes / methods of working being explored.  Audit will provide appropriate follow up and advice and support in the establishing of processes for this revised delivery;

- ICT Reviews – this is due to the significant changes being made within ICT Services and the development of the Digital Strategy and the completion of the Data Recovery and Business Continuity plan.  Sufficient resource will be supplied to satisfy the Annual Governance Statement.

There are also 2 pieces of work that will not be completed in 2018/19 due to time constraints; they are:-

- Project Management Information – this work will start mid-March but will not be completed until early April 2019/20.  This reflects the approval of the Corporate Plan at Full Council and InPhase being uploaded with the full project plan;

- Shared Assurance Services Creditors – this work will be carried forward into April 2019/20, this does not cause significant risk to either Authority as the service has been audited on an annual basis and achieves a Substantial / Full Assurance Rating each year.  Creditors for 2018/19 will be reflected in the accounts which is subject to external audit.  Therefore in early 2019/20 Internal Audit will provide greater assurance in that area.

6.4	The following table outlines the main pieces of work undertaken in the last period:-

| Audit Area | Assurance Rating | Comments |
| --- | --- | --- |
| South Ribble Council |
| Council Tax | Full | Only minor issues were identified as part of the review, all management actions were implemented prior to completion of the review. |
| NDR | Full | Only minor issues were identified as part of the review, all management actions were implemented prior to completion of the review. |
| General Data Protection Regulations (GDPR) | Not applicable | Internal Audit are providing ongoing support as part of the project group who are implementing GDPR. The Data Protection Policy has been reviewed and updated along with the production of a Data Breach Policy. These policies are provided as a separate report to the Governance Committee. |
| Shared Financial Services (South Ribble) |
| Treasury Management | Substantial | This report has been produced by LCC, Management Actions are to be discussed before the end of March. |

7.   	Financial implications

  - There are no financial implications.

8.    	LEGAL IMPLICATIONS

8.1	There are no legal implications.

9. 		OTHER IMPLICATIONS:

9.1	The matters raised in the report are cross cutting and impact upon those individual services reviewed and the Internal Control environment of the Council.

9.2	Failure to report the progress of the Audit Plan to the Governance Committee could result in the lack of awareness of those charged with the responsibility for the Governance of the Council of issues in regard to the Council’s overall control environment.  This could result in financial, legal and / or reputational harm to the Council.

13. 	BACKGROUND DOCUMENTS (or There are no background papers to this report)

South Ribble Internal Audit Plan 2018/19
Shared Financial Services Audit Plan 2018/19

14. 	APPENDICES (or There are no appendices to this report

Appendix 1 – Audit Plan Progress Report for South Ribble Council and Shared Financial Services elements.

| Report Author: | Telephone: | Date: |
| --- | --- | --- |
| Janice Bamber Interim Head of Shared Assurance | 01772 625272 | 4 March 2019 |

APPENDIX 1

INTERNAL AUDIT PLANS 2018/19

SOUTH RIBBLE COUNCIL

| WORK AREA | RISK | QTR | EST (Days) | ACT | BAL | NOT REQ | C/f | REVIEW STATUS | ASSURANCE RATING | STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AUDIT PLANNED WORK |
| RESOURCES & TRANSFORMATION |
| Legal, Democratic & HR Services |
| Licensing Service | MAJOR | 1 | 15 | 13.2 | 0 | 0 |  | COMPLETED | SUBSTANTIAL | Completed |
| Payroll / HR System Data Testing | N/A | 4 | 5 | 0 | 0 | 5 |  | COMPLETED |  | To be reported as part of Shared Assurance Payroll Review |
| Policy, Communications, Customer, Digital & Strategic Asset Management |
| Performance Management Information | CRITICAL | 4 | 10 | 12.1 | 0 |  |  | Testing in progress Completed 8/03/19 |  | Testing is completed, Draft Report produced by 8/03/19 |
| Project Management | CRITICAL | 3 | 15 | 1 | 0 |  | 14 | Scope identified c/f 2019/20 |  | Work will commence in March will be completed 2019/20 |
| Council Tax | CRITICAL | 3 | 10 | 9.7 | 0 |  |  | COMPLETED | FULL | Audit review initially classified Council Tax systems as Substantial, however, implementation of the Management Actions has resulted in a revised Assurance Rating. |
| Non-Domestic Rates (NDR) | CRITICAL | 3 | 10 | 10.8 | 0 |  |  | COMPLETED | FULL | Audit review initially classified NDR systems as Substantial, however, implementation of the Management Actions has resulted in a revised Assurance Rating. |
| Housing Benefits | CRITICAL | 2&3 | 10 | 10.4 | 0 |  |  | COMPLETED | FULL | Report is completed, Management Actions implemented prior to completion of audit work |
| Sundry Debtors | CRITICAL | 3 | 10 | 9.3 | 0 |  |  | COMPLETED | FULL | Report is completed, Management Actions implemented prior to completion of audit work. |
| ICT Review | CRITICAL | 2&3 | 15 | 0.4 | 0 |  | 14.6 | c/f to 2019/20 |  | Significant changes to ICT, audit work to be carried forward into 2019/20 |
| REGENERATION & GROWTH |
| Neighbourhoods & Development |
| Health & Safety | CRITICAL | 2&3 | 10 | 2.4 | 7.6 |  |  | Scope Agreed and work commenced |  | Work undertaken by management in respect of compliance with Framework. Audit work will be completed by mid-March and reported. |
| Refuse Collection & Recycling Contract | CRITICAL | 2 | 10 | 11 | 0 |  |  | COMPLETED | SUBSTANTIAL | Completed |
| My Neighbourhoods | MAJOR | 3&4 | 10 | 1.3 | 0 |  | 8.7 | c/f 2019/20 |  | Review of service being undertaken, work to be carried forward to 2019/20 |
| Planning & Property |
| Property Repairs & Maintenance | CRITICAL | 3 | 15 | 5.9 | 9.1 |  |  | Work completed, Awaiting Report |  | Management have produced an Improvement Plan agreed by Leadership Team, further work will be undertaken in 2019/20 to monitor compliance. |
| Commercial Properties | MAJOR | 2&3 | 15 | 3.9 | 11.1 |  |  | Testing ongoing |  | Testing commenced, Work complete by end of March |
| TOTAL PLANNED WORK |  |  | 160 | 91.4 | 27.8 | 5 | 37.3 |  |  | % of Audit Planned work completed in Year = 74.5% |
| Actual Plus Balance Sub Total |  |  |  |  | 119.2 |  |  |  |  |  |
| Actual Plus Bal plus c/f |  |  |  |  |  |  | 156.5 |  |  | % of Audit Planned work Completed =97.8% |

| ONGOING WORK THROUGHOUT THE YEAR |
| --- |
| CORPORATE |
| Annual Governance Statement | N/A | 1&4 | 20 | 14.8 | 0 | 5.2 |  | Completed | N/A | 2017/18 AGS Completed |
| Anti-Fraud & Corruption | N/A | ALL | 10 | 1.7 | 0 | 8.3 |  | Ongoing updates | N/A | Ongoing policy updates, fraud alerts circulated during 2018/19 |
| National Fraud Initiative (NFI) | N/A | ALL | 15 | 18.7 | 0 | 0 |  | Data Sets submitted | N/A | Data Sets submitted, CTAX / Elec Reg. SPD results returned & being investigated Further results for other data sets available from end of January results reported to Gov. Cttee. 2019/20 |
| PROJECT GROUPS |
| Legal, Democratic & HR Services |
| GDPR Implementation | N/A | 1 | 5 | 15.9 | 0 |  |  | Project Support | N/A | GDPR Implementation group meets weekly to update on progress. Ongoing advice & support provided re policies and procedures |
| Planning & Property |
| City Deal | N/A | ALL | 5 | 1.3 | 0 | 3.7 |  | COMPLETED | N/A | Project Group Audit role advice & support completed |
| Investment Strategy | N/A | ALL | 5 | 0.4 | 0 | 4.6 |  | COMPLETED | N/A | Project Group Audit role advice & support completed |
| Housing Development | N/A | ALL | 5 | 0.3 | 0 | 4.7 |  | COMPLETED | N/A | Project Group Audit role advice & support completed |
| Neighbourhoods & Development |
| Health, Leisure & Wellbeing Campus | N/A | ALL | 5 | 0.5 | 0 | 4.5 |  | COMPLETED | N/A | Project Group Audit role advice & support completed |
| TOTAL CONTINUOUS WORK |  |  | 70 | 53.6 | 0 | 31 |  |  |  |  |
| WORK OUTSIDE AUDIT PLANNING PROCESS |
| GENERAL |
| Residual Work from 2017/8 | N/A | 1 | 20 | 7.1 | 0 | 12.9 |  | COMPLETED | N/A |  |
| GRACE System Administration | N/A | ALL | 20 | 20.6 | 0 | 0 |  | COMPLETED | N/A |  |
| Business Continuity | N/A | ALL | 30 | 0.9 | 0 | 29.1 |  | COMPLETED | N/A |  |
| Post Audit Reviews | N/A | ALL | 10 | 1 | 0 | 9 |  | COMPLETED | N/A |  |
| Contingency / Irregularities | N/A | ALL | 15 | 19.6 | 0 | 0 |  | COMPLETED | N/A |  |
| Governance Committee | N/A | ALL | 15 | 7.4 | 0.6 | 7 |  | COMPLETED | N/A |  |
| TOTAL WORK OUTSIDE PLAN |  |  | 110 | 56.6 | 0.6 | 58 |  |  |  |  |
| SUB TOTAL Ongoing Work & Work outside plan |  |  | 180 | 110.2 | 0.6 | 89 |  |  |  |  |
| TOTALS |  |  | 340 | 201.6 | 28.4 | 94 | 37.3 |  |  |  |
| TOTAL Actual Plus Balance to be completed |  |  |  |  | 230 |  |  |  |  | % of Audit Planned work completed in Year = 67% However 27.64% of Work Completed under budget |
| Actual + Balance + c/f |  |  |  |  |  |  | 267.3 |  |  | % of Audit Work Completed 78% |
| Carried forward 2019/20 |  |  |  |  |  |  |  |  |  |  |
| ICT Reviews |  |  |  |  | 15 |  |  |  |  |  |
| Project Management |  |  |  |  | 14 |  |  |  |  |  |
| My Neighbourhoods |  |  |  |  | 8.7 |  |  |  |  |  |

SHARED FINANCIAL SERVICES

| WORK AREA | RISK | QTR | EST (Days) | ACT | BAL | NOT REQ | C/F | REVIEW STATUS | ASSURANCE RATING | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Treasury Management | CRITICAL | 3 | 20 | 20 |  |  |  | COMPLETED |  | LCC Completed Audit work, Draft Report produced; Head of Audit & Assurance to review working papers & report by 26/01/19 |
| Payroll | CRITICAL | 4 | 20 | 6.3 | 13.7 |  |  | Testing in Progress |  | Work in Progress, work will be completed by end of March. |
| Creditors | CRITICAL | 4 | 20 | 0.7 | 0 |  | 20 | C/F 2019/20 |  | Work will be carried forward to April 2019/20 |
| Main Accounting | CRITICAL | 4 | 20 | 13 | 0 | 7 |  | DRAFT REPORT |  | Draft Report Produced, Issued by 15/03/19. |
| Cash & Bank | CRITICAL | 4 | 20 | 8.2 | 11.8 |  |  | Partially complete |  | Work on Chorley Cash & Bank complete, South Ribble to be completed by end of March |
| Residual Work from 2017/18 | N/A | 1 | 15 | 18 | 0 |  |  | COMPLETED | N/A | Completed |
| GRACE System Administration | N/A | ALL | 5 | 3.9 | 0 |  |  | COMPLETED | N/A |  |
| Post Audit Reviews | N/A | ALL | 10 | 0 | 0 |  |  | COMPLETED | N/A |  |
| Contingency / Irregularities | N/A | ALL | 10 | 9.2 | 0 |  |  | COMPLETED | N/A |  |
| TOTALS |  |  | 140 | 79.3 | 25.5 | 7 | 20 |  |  | % of Shared Assurance Plan completed in Year = 74.86% |
| Actual plus balance to be completed |  |  |  |  | 104.8 |  |  |  |  |  |
| Actual + balance + c/f |  |  |  |  |  |  | 124.8 |  |  | % of Shared Assurance Plan completed = 89.14% |
| Work c/f 2019/20 |  |  |  |  |  |  |  |  |  |  |
| Creditors |  |  |  |  | 19.3 |  |  |  |  |  |