| REPORT TO | ON |
| --- | --- |
| CABINET | 20 March 2019 |
| TITLE | PORTFOLIO | REPORT OF |
| Corporate Performance Report at the end of Quarter 3 (31st December 2018) | Council Leader | Chief Executive |

| Is this report a KEY DECISION (i.e. more than £100,000 or impacting on more than 2 Borough wards?) Is this report on the Statutory Cabinet Forward Plan? Is the request outside the policy and budgetary framework and therefore subject to confirmation at full Council? Is this report confidential? | No No No No |
| --- | --- |

# PURPOSE OF THE REPORT

# This report provides an overview of performance against the Council’s Corporate Plan for 2018-19 at the end of the third quarter i.e. the end of December 2018.

# PORTFOLIO RECOMMENDATIONS

3.  CORPORATE PRIORITIES

# The report relates to all of the corporate priorities as shown below.

| Excellence and Financial Sustainability | ( | Health and Wellbeing | ( |
| --- | --- | --- | --- |
| Place | ( | Our People | ( |

# 4.   BACKGROUND TO THE REPORT

The Corporate Plan for 2018-19 contains a number of projects for delivery across the financial year. This report provides an update for Quarter 3 on both the Projects, and the key Performance indicators agreed by this council.

Performance reports for each quarter are considered by the Council’s Leadership Team and for Quarters 1, 2, 3 and 4 by the Cabinet and the Council’s Scrutiny Committee. An annual report on performance at the end of Quarter 4 will also be submitted to Full Council.

Performance for each project is categorised into one of three categories, shown in the below table.

| Improved performance/ delivery which is on target or improved. | Performance/ delivery which has stayed the same, or changed in performance with a minor variance. | Performance / delivery which has dropped or cannot be delivered within previously agreed timescales. |
| --- | --- | --- |

# 5.	PERFORMANCE AT THE END OF QUARTER 3

5.1   PROJECTS

5.1.1 Below sets out a dashboard of the performance of projects for third quarter of 2018-19. Detailed analysis is provided in Appendix 1.  As a headline summary, in Quarter 3, 42 project are green, 2 are amber and 2 are red. This is a highly ambitious programme of works for this council to deliver which requires all officers to work to the principles of a high performing team.

Please see overleaf:

5.1.2	Key achievements to note

- Within Worden Park development work is underway on multiple improvements, including the conservatory, arboretum, craft centre, and toilets.

- The ICT Strategic Review (Digital Strategy Review) project is now completed and the outcomes will be used to inform the direction of travel for ICT at the council.

- The Mental Health 2000 awareness project has been completed.

- The Clean Air action Plan has now been developed and approved by Cabinet.  Some examples of what will be done as part of the plan to improve air quality is listed below -

    - Anti-Idling Campaign in declared Air Quality Management Area’s (AQMA) and outside schools, colleges and leisure centres

    - Continuing  the ‘Bike to work’ salary sacrifice scheme

    - Working with taxi firms to encourage the uptake of low emission vehicles (Electric)

    - Publicise and encourage use of the Lancashire based Air Quality Guidance Documents for Developers

    - Systematically review and replace the councils vehicle fleet with low emission vehicles (Electric)

This is not an extensive list of actions on the air quality plan and it should be noted that many of the solutions remain with partners undertaking key roles and responsibilities.”

- The Green Links programme is well underway, with significant consultation events being planned for the next quarter.

- Successful completion of the WW1 Centenary McNamara memorial and the Walton-le-dale car park, with great community engagement events around Centenary Remembrance Day.

- A Volunteering Strategy has recently been presented to council, and the council will now consult with our partners and volunteers to develop this further.

- The programme to update the Civic Centre (Banqueting Suite) rooms and the AV equipment has been completed and monitoring is taking place. The works include:

    - The modernisation the Shield, Wheel and Cross rooms

    - Renovation of toilets in the conference and business area

    - New glazing

    - Creation of two syndicate meeting rooms

    - New audio visual equipment.

A business plan has been developed which covers a range of issues concerned with future direction of travel for the Civic centre.

- The project to ‘Develop South Ribble Programme for festivals and Events’ has been completed successfully for 2018/19.  Planning for next year’s events (2019/20) is currently underway.

- A Borough wide Community Strategy has been developed and noted by full Council in January 2019.

5.1.3	Exceptions to note

- The Depot Commercialisation Phase 1 project is amber due to a delay with alterations. The mezzanine floor and waiting room have been constructed. The remaining alterations is due to commence in the next few weeks. However it should be noted that there has been considerable success in working up a new commercial model with our partners FCC Environment, which has had a positive impact on service delivery and our commercial approach.

- The Cuerden Strategic Site programme has been set back. Lancashire County Council are the lead on the project and we are still awaiting formal notification of a delivery programme and timescales.

- The development of the Central Lancashire Economic strategy is being developed as a supporting document for the new core strategy.

- The development of a formal South Ribble Ambassador programme has been delayed, although discussions have started to take place with Business and our partners. This item will need to be refreshed once the elections have taken place.

- The project of the new Ribble crossing will require Lancashire wide buy-in as a sub-regional and regional significant project.  Officers are continuing to explore all funding options.

5.2   PERFORMANCE INDICATORS

5.2.1 With regards to performance indicators, the council currently measures 61 indicators, over an annual period, which are each categorised into one of the Council’s four Corporate Priorities.

A detailed review of the Indicators for Quarter 3 are set out in Appendix 1, with a summary below showing that within the third quarter of the total of 29 indicators that can be reported 15 are green, 5 are  amber, and 2 are red.  We have 7 indicators which have recently been introduced, and therefore, at this stage, either have no data points approved as they are still being developed, or there is no comparable data to test performance.  This must however be collated and reported, so members are aware the information, and that it will be available for comparison in future years.

| No. of measures | Green | Amber | Red | No. with no comparable data or contextual data only |
| --- | --- | --- | --- | --- |
| 29 | 15 | 5 | 2 | 7 |

5.2.2 	Key achievements to note

- The % of missed domestic waste bin collections has continued to maintain its exceptional standard of 0.02%.

- There has been a decrease in the number of accidents reported to HSE arising from work activity from 3 in quarter 2 to 0 in quarter 3.

- The number of visits to our leisure and sports facilities has increased in quarter 3 (172,045), compared to the same time last year (171,308). This has been an increase of 737 visitors which is a result of a rise in gym usage and stable year on year usage on both swimming lessons and gymnastics lessons.

- The number of staff undertaking apprenticeships in the council has maintained its high performance of 12 apprenticeship positions.  The levels of apprenticeships range from level 3 to level 6 from various providers. A breakdown of apprenticeships and providers are shown below:

| Apprenticeship | Count | Level | Provider |
| --- | --- | --- | --- |
| Construction Technical and Professional | 1 | 3 | WIGAN AND LEIGH COLLEGE |
| Construction Management | 1 | 4 | PRESTON COLLEGE |
| Chartered manager degree apprenticeship | 1 | 6 | UNIVERSITY OF CENTRAL LANCASHIRE |
| Construction Management | 1 | 4 | WIGAN AND LEIGH COLLEGE |
| Horticulture and Landscape Operative | 2 | 2 | MYERSCOUGH COLLEGE |
| Learning and Development | 1 | 3 | INTEC BUSINESS COLLEGES LIMITED |
| Heavy vehicle service and maintenance technician (Standard) | 1 | 3 | PRESTON COLLEGE |
| Chartered Surveyor | 3 | 6 | UNIVERSITY OF SALFORD (1) UNIVERSITY OF CENTRAL LANCASHIRE (2) |
| HR Support Officer | 1 | 3 | TRAFFORD COLLEGE |

The Apprentice Factory is a long term project, which will run throughout the five year Corporate Plan period, supporting delivery of City Deal targets and corporate targets in a phased approach as set out in the Apprentice Factory Development Plan. The Apprentice Factory has sourced access to half a million pounds training for council employees, which, to date, has been delivered at no cost to the Council. Year 2 of the Apprentice Factory includes plans to bid for unspent levy funds from companies within the borough of South Ribble so that levy funds are reinvested within the borough and will underpin further development plans and roll out with external businesses in South Ribble.  There are also plans for the Apprentice Factory to work in collaboration with Runshaw College to raise awareness of T-Levels prior to its implementation in 2020.

- Homeless presentations is down this quarter, from quarter two which is a key success (down from 88 to 85).  The future yearly comparison figures may take some time to adjust due to changes to the law in April 2018 with work being undertaken with our prevention partner “Key” and the homelessness team.

    - Exceptions to note

- The number of complaints has increased by 6 this quarter.  There is no obvious trend as the complaints encompass a wide range of departments and subject matters. A breakdown of complaints by department can be seen below:

| Department | Number of Complaints |
| --- | --- |
| Benefits | 5 |
| Planning | 4 |
| Gateway | 3 |
| Neighbourhoods | 3 |
| Community Works | 2 |
| Total | 17 |

- We are now ensuring that we record the compliments that are received, this figure is 11 for quarter 3 (down from 15 compliments received in quarter 2), and a breakdown of compliments by department can be seen below:

| Department | Number of Compliments |
| --- | --- |
| Gateway | 4 |
| Neighbourhood Services | 4 |
| Environmental Health | 2 |
| Community Involvement | 1 |
| Total | 11 |

- The capital budget variances will be picked up in the financial report.

- The number of young people taking part in programmed school and out of school activities has decreased since last term. This is due to timetabling of activities and the time of year. The figures last period were higher because the Council ran a Dance from the Heart Project and our Active camps throughout the summer period.

- The Licensing Team have commenced a process of carrying out more in depth premises inspections. This has involved more multi-agency operations involving the Home Office (Immigration), the Fire Service, the Gambling Commission and the Police. Such operations have resulted in three formal reviews of premises licences. We are adopting a more holistic approach to enforcement. We are also becoming more outcome focused. We have also been extending enforcement activities to test purchases of an evening (e.g. under age sales). This has resulted in a slight decrease in the numbers of premises being inspected and the numbers of vehicle inspections of licensed taxis (from 24 – 21).

6.   CONSULTATION CARRIED OUT AND OUTCOME OF CONSULTATION

N/A

- OTHER OPTIONS CONSIDERED

N/A

- Financial implications

The financial implications arising from this report are reported in the third quarter budget monitoring paper.

- Human Resources and Organisational Development implications

The delivery of the corporate plan, and its performance is totally dependent on the officers of this council and their commitment in delivering quality services. It is pleasing to note that this staff commitment is presenting itself in a positive performance report, which on balance, provides assurance that services are being delivered efficiently and effectively.

- ICT/technology implications

ICT or technology also plays a significant role in effective service delivery. Moving forward, the council will capture any further efficiency of service delivery within its Digital strategy.

- Property and Asset Management implications

The Council is currently reviewing the office accommodation for all officers, along a review of all technology, plant and machinery.  Effective, high performing teams excel when they work in a quality environment and have quality tools.  The corporate plan identifies specific projects that will deliver this environment, and these are reported with this report.

- RISK MANAGEMENT

The Corporate Risk Register at the end of Quarter 3 shows 5 risks with a residual risk rated as green and 4 with a residual risk rated as amber. There are currently no risks with a residual risk rating as red at the end of this quarter.

- EQUALITY AND DIVERSITY IMPACT

The Corporate plan has set out its equality and impact, which is reported to members in line with its corporate planning process.

- COMMENTS OF THE STATUTORY FINANCE OFFICER

The report highlights the significant progress being made in project development which is supported through the Councils Medium Term Financial Strategy.  Project officers continue to embed transformation into their work programmes such that these significant investments contribute to Corporate Priorities in particular Excellence and Financial Sustainability.

- COMMENTS OF THE MONITORING OFFICER

It is the established practice of the council to report openly and transparently on our level of performance with regard to our Corporate Plan. Clearly it is important to provide members and the general public confidence that we are indeed delivering on our priorities. In this regard there are no issues that the Monitoring Officer needs to raise.

- RELEVANT DIRECTORS RECOMMENDATIONS

It is recommended that:

- Members note performance throughout Quarter 3 shown at Appendix 1.

- Members note the corporate risks and the controls that have been in place to mitigate risks in 2018-19 as identified in the Corporate Risk Register shown at Appendix 2.

- BACKGROUND DOCUMENTS

- Corporate Plan 2018-19

Appendix 1: Quarter 3 Performance Report

Appendix 2: Corporate Risk Register

| Report Author: | Telephone: | Date: |
| --- | --- | --- |
| Michael Johnson / Heather McManus | 01772 (62) 5339 | 26/02/2019 |